## Def. Maint. Costs Total
Miles Community College Building Survey 2016 Deferred Maintenance Costs - TOTAL
Location | Summary Item | Description | Priority | Quantity | Unit | Unit Cost | Total | Item Subtotal | Bldg Subtotal
Campus & Site | 1 | Develop Moorehead | 3 |  |  |  | By City
Campus & Site | 2 | Develop S Sewell by Track and Centra | 2 | 600 | l.f. | 500 | 300000
Campus & Site | 2 | Develop S Sewell from Batchelor to Comstock | 2 |  |  |  | By City | 300000
Campus & Site | 3 | Bridge St. Curb & Gutter east of S. Sewell N side | 3 | 750 | l.f | 20 | 15000
Campus & Site | 3 | Dedicated bus parking on Bridge St. by track S. side | 3 | 6000 | sf | 25 | 150000
Campus & Site | 3 | Bridge St. Curb & Gutter east of S. Sewell by Track | 3 | 800 | l.f | 20 | 16000 | 181000
Campus & Site | 5 | Expand S Quads Parking | 3 | 4250 | sf | 10 | 42500
Campus & Site | 5 | Develop East Centra Parking | 3 | 45000 | sf | 10 | 450000 | 492500
Campus & Site | 6 | Develop Track Pkg. @ Armory | 2 | 7000 | sf | 10 | 70000
Campus & Site | 6 | Campus Sidewalk Demo & Replacement | 2 | 1500 | s.f. | 12 | 18000 | 88000
Campus & Site | 7 | Campus Outdoor Lighting | 3 | 40 | ea. | 3500 | 140000
Campus & Site | 8 | Develop French drains, or wells for roof downspouts | 3 | 58 | ea. | 2500 | 145000
Campus & Site | 8 | Grade and develop retention ponds | 3 | 6 | ea. | 7500 | 45000 | 190000
Campus & Site | 9 | Building Access Controls | 3 | 25 | ea. | 5500 | 137500
Campus & Site | 9 | Outdoor Call Stations | 3 | 7 | ea. | 7000 | 49000
Campus & Site | 9 | Wall Mtd. Call Stations | 3 | 4 | ea. | 3800 | 15200
Campus & Site | 9 | Restrictive Traffic Bollards | 3 | 24 | ea. | 500 | 12000
Campus & Site | 9 | Traffic Gates w/ Access Controls | 3 | 4 | ea. | 9000 | 36000 | 249700
Campus & Site | 10 | Sidewalk parallel to S. Sewell | 3 | 3500 | sf | 8 | 28000
Campus & Site | 10 | Disc Golf Course | 3 | 18 | ea. | 750 | 13500
Campus & Site | 10 | SE to Track path | 3 | 700 | l.f. | 48 | 33600 | 75100
Campus & Site | 11 | Modify Irrigation to Drip | 3 | 40 | ea. | 100 | 4000
Campus & Site | 11 | Plant Trees | 3 | 30 | ea. | 400 | 12000
Campus & Site | 12 | Install Generator for Essential systems at Admin., Student Services, Centra | 3 | 3 | ea. | 100000 | 300000
Campus & Site | 12 | Underground LPG storage for Centra, Student Services and Admin | 3 | 5000 | gal | 5 | 25000
Campus & Site | 12 | 100 KW Solar Array & Controller | 3 | 100000 | watt | 1.9 | 190000
Campus & Site | 12 | New Building Sign Package | 3 | 20 | ea. | 1500 | 30000
Campus & Site | 12 | Fix Fence @ Dirt Pkg Lot/Track | 3 | 1 | l.s. | 800 | 800 | 545800 | 2278100
0
Classroom & Admin. | 13 | Sidewalk Replacement | 1 | 100 | s.f. | 10 | 1000 | 1000
Classroom & Admin. | 14 | Add Gutters & Downspouts | 1 | 452 | l.f. | 6 | 2712
Classroom & Admin. | 14 | Re-grade N side of bldg. | 1 | 190 | c.y. | 32 | 6080 | 8792
Classroom & Admin. | 15 | ReDo Courtyard ramp/walks | 1 | 1 | l.s. | 7500 | 7500
Classroom & Admin. | 15 | Infill W Entry Mud Scrapers | 1 | 2 | ea. | 250 | 500
Classroom & Admin. | 15 | Modify Men's RR Stalls | 1 | 3 | ea. | 1500 | 4500
Classroom & Admin. | 15 | Modify Men's RR Entry | 1 | 1 | ea. | TBD | TBD | 12500
Classroom & Admin. | 16 | Coat Roof | 1 | 37332 | s.f. | 4 | 149328
Classroom & Admin. | 17 | Replace Entry Systems | 2 | 450 | s.f. | 90 | 40500
Classroom & Admin. | 18 | Insulate Exterior Walls | 2 | 9500 | s.f. | 10 | 95000
Classroom & Admin. | 19 | Misc Lay In Clng Replacement | 3 | 1 | l.s. | 8500 | 8500
Classroom & Admin. | 20 | Courtyard Landscape & ReDo | 3 | 1 | l.s. | 30000 | 30000
Classroom & Admin. | 21 | Pipe insulation & Wrap | 2 | 1 | l.s. | 1500 | 1500
Classroom & Admin. | 21 | Replace HID Wall Packs | 2 | 6 | ea. | 500 | 3000
Classroom & Admin. | 21 | Repair Masonry Sign | 2 | 1 | l.s. | 2500 | 2500 | 7000 | 352620
0
Student Services | 22 | E. Sidewalk Replacement | 2 | 400 | s.f. | 8 | 3200
Student Services | 22 | W. Sidewalk Replacement | 2 | 800 | s.f. | 8 | 6400
Student Services | 22 | W. Patio Walk Edge Slope | 2 | 100 | l.f. | 40 | 4000 | 13600
Student Services | 23 | Engineered Fill E. Side | 2 | 40 | c.y. | 35 | 1400
Student Services | 23 | Relocate W. Roof Drains | 2 | 4 | ea. | 2500 | 10000 | 11400
Student Services | 24 | Replace W Hall Exterior Brick | 2 | 60 | s.f. | 25 | 1500
Student Services | 24 | R&R E Wainscot Brick | 2 | 380 | s.f. | 35 | 13300 | 14800
Student Services | 25 | R&R W Alum Entry System | 2 | 132 | s.f. | 90 | 11880
Student Services | 25 | Overhaul E. Doors | 2 | 2 | ea. | 800 | 1600 | 13480
Student Services | 26 | Adjust N Café Doors | 2 | 2 | ea. | 250 | 500
Student Services | 27 | Mud Jack E. Café/Bookstore | 1 | 1 | l.s. | 150 | 8000
Student Services | 27 | R&R Kitchen Flooring | 1 | 830 | s.f. | 11 | 9130 | 17130
Student Services | 28 | R&R &Raise Kitchen Ceiling | 3 | 830 | s.f. | 5 | 4150
Student Services | 29 | P&P Kitchen E Wall | 2 | 1 | l.s. | 2500 | 2500
Student Services | 29 | Doorknob Hole W Closet | 2 | 1 | l.s. | 150 | 150 | 2650
Student Services | 30 | R&R Range Hood/Upgrade | 1 | 1 | l.s. | 30000 | 30000
Student Services | 30 | Complete Kitchen Overhaul | 1 | 1 | ea. | TBD | TBD | 30000 | 107710
0
Centra | 31 | Repair walks for even grades | 1 | 1 | l.s. | 4000 | 4000
Centra | 31 | Modify Men's RR Stalls | 1 | 2 | ea. | 1500 | 3000
Centra | 31 | Install Exterior Elevator & Shft | 1 | 1 | l.s. | 125000 | 125000
Centra | 31 | R&R Racquetball Doors | 1 | 4 | ea. | 1800 | 7200
Centra | 31 | Install ADA/Braille Signage | 1 | 22 | ea. | 30 | 660 | 139860
Centra | 32 | Change & Extend N Landing | 2 | 70 | s.f. | 8 | 560
Centra | 33 | Eng. Fill and Grade N Side | 2 | 135 | c.y. | 32 | 4320
Centra | 34 | Prep and Paint CMU Walls | 2 | 4600 | s.f. | 3 | 13800
Centra | 34 | Seal wall Penetrations | 1 | 1 | l.s. | 800 | 800
Centra | 34 | Apply EIFS to Lower CMU | 2 | 4600 | s.f. | 14 | 64400
Centra | 34 | Add Insulation to Upper Walls | 2 | 10800 | s.f. | 8 | 86400 | 169720
Centra | 35 | Replace Windows | 2 | 192 | s.f. | 75 | 14400
Centra | 35 | Exterior Shade for S windows | 2 | 24 | l.f. | 200 | 4800 | 19200
Centra | 36 | N Side Gutters & Snow Grds | 3 | 180 | l.f. | 20 | 3600
Centra | 36 | N Side Snow Guards | 3 | 360 | ea. | 10 | 3600
Centra | 36 | Heat Tape all Downspout Ldr | 3 | 10 | ea. | 500 | 5000 | 12200
Centra | 37 | Addition w/ Airlocks to Auditor. | 2 | 1 | ea. | TBD | TBD
Centra | 38 | Replace Main Floor Carpet | 2 | 1664 | s.f. | 6 | 9984
Centra | 38 | Clean & Seal Bare Concrete | 2 | 1 | l.s. | 800 | 800 | 10784
Centra | 39 | Modify Fire Sprinklers | 1 | See M&E |  | TBD | TBD
Centra | 40 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1500 | 1500
Centra | 41 | Change Doors to ADA Hrdwr. | 2 | 17 | ea. | 500 | 8500
Centra | 42 | Re-insulate Foundation | 2 | 1600 | s.f. | 6 | 9600
Centra | 43 | Crows Nest Staircase | 1 | 1 | l.s. | 8500 | 8500
Centra | 43 | Enclose Hall to Crows Nest | 1 | 1 | l.s. | 10000 | 10000
Centra | 43 | HVAC for Crows Nest | 1 | See M&E |  | TBD | TBD | 18500
Centra | 44 | Dedicated Track Restrooms | 3 | 2 | ea. | 60000 | 120000
Centra | 45 | Seal East drive & parking | 3 | 3000 | s.f. | 2.5 | 7500
Centra | 45 | R&R Heavy Pave E. Side |  | 8000 | s.f. | 10 | 80000 | 87500 | 597924
0
Vo-Tech | 46 | R&R Main Entry Landing | 2 | 144 | s.f. | 8 | 1152
Vo-Tech | 46 | Change Door Hrdwr to ADA | 2 | 23 | ea. | 500 | 11500
Vo-Tech | 46 | New Unisex ADA Restroom | 2 | 1 | l.s. | 25000 | 25000 | 37652
Vo-Tech | 47 | Regrade Landscape to Drain | 2 | 1 | l.s. | 2500 | 2500
Vo-Tech | 47 | Modify bottom of Ramp/Gutter | 1 | 1 | l.s. | 2500 | 2500 | 5000
Vo-Tech | 48 | Repair or Remove Ext. Walls | 3 | 1 | l.s. | 4500 | 4500
Vo-Tech | 49 | Replace all windows | 1 | 185 | s.f. | 75 | 13875
Vo-Tech | 50 | Roof Coating (in 15 yrs out) | 3 | 18570 | s.f. | TBD | TBD | TBD
Vo-Tech | 51 | New Seals on Exterior Doors | 1 | 10 | ea. | 200 | 2000
Vo-Tech | 51 | Replace OH Doors & Opnrs. | 1 | 3 | ea. | 8500 | 25500 | 27500
Vo-Tech | 52 | Replace Windows | 1 | 185 | s.f. | 75 | 13875
Vo-Tech | 52 | Replace Fndn. Insulation | 1 | 1968 | s.f. | 4 | 7872
Vo-Tech | 52 | Apply EIFS to Exterior Walls | 2 | 7800 | s.f. | 14 | 109200 | 130947
Vo-Tech | 53 | Clean & Caulk Joints | 3 | 448 | l.f. | 4 | 1792
Vo-Tech | 53 | Repair Damaged Sheet Vinyl | 3 | 15 | ea. | 150 | 2250
Vo-Tech | 54 | Fix Fire Taping Upper Walls | 1 | 160 | l.f. | 5 | 800
Vo-Tech | 54 | Prep and Paint Shop Walls | 2 | 7400 | s.f. | 2 | 14800 | 15600
Vo-Tech | 55 | Prep and Paint Shop Clngs. |  | 8320 | s.f. | 2 | 16640
Vo-Tech | 55 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1500 | 1500 | 18140
Vo-Tech | 56 | New Door Seals Entry Doors | 1 | 2 | ea. | 250 | 500
Vo-Tech | 56 | New HM Door on Mech Room | 1 | 1 | ea. | 1500 | 1500
Vo-Tech | 56 | Adjust & R&R Closers | 1 | 10 | ea. | 150 | 1500
Vo-Tech | 56 | Electric Door Hold Opens | 1 | 4 | ea. | 1500 | 6000 | 9500
Vo-Tech | 57 | Install Exit Signs | 1 | 6 | ea. | 500 | 3000
Vo-Tech | 58 | Replace Damaged Ashpalt | 2 | 500 | s.f. | 8 | 4000
Vo-Tech | 58 | Clean & Seal Asphalt Paving | 2 | 9700 | s.f. | 2.5 | 24250
Vo-Tech | 58 | Extend Paving to South | 3 | 24000 | s.f. | 6 | 144000
Vo-Tech | 58 | Fence Around S Lot/Parking | 3 | 500 | l.f. | 30 | 15000 | 187250
Vo-Tech | 59 | Fixed Mezzanine Stairs | 1 | 2 | ea. | 3500 | 7000 |  | 464006
0
Library Addition | 60 | Re-Route Downspout | 1 | 1 | l.s. | 1500 | 1500
Library Addition | 60 | R&R SW Walk | 2 | 512 | s.f. | 8 | 4096 | 12596
Library Addition | 61 | Install Heat Tape in Gutter/DS | 2 | 1 | l.s. | 1500 | 1500
Library Addition | 61 | Modify SW corner Landscape | 2 | 1 | l.s. | 1800 | 1800 | 3300
Library Addition | 62 | Install Roof Hatch & Ladder | 2 | 1 | l.s. | 6500 | 6500
Library Addition | 63 | R&R Panel 15 over Windows | 2 | 520 | s.f. | 20 | 10400
Library Addition | 64 | R&R Windows | 2 | 420 | s.f. | 75 | 31500
Library Addition | 65 | R&R Roof | 1 | 22000 | s.f. | 8.5 | 187000
Library Addition | 67 | Add Rigid Insulation to Roof | 2 | 22000 | s.f. | 3.25 | 71500
Library Addition | 67 | Insulate Foundation | 2 | 1404 | s.f. | 4 | 5616 | 77116
Library Addition | 68 | R&R Carpet Library | 3 | 4800 | s.f. | 6 | 28800
Library Addition | 69 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1200 | 1200 |  | 351412
0
Auditorium Addition | 71 | R&R Settled Walk E Side | 1 | 1 | l.s. | 1200 | 1200
Auditorium Addition | 71 | Install Splash Blocks | 2 | 8 | ea. | 100 | 800
Auditorium Addition | 71 | Patch in Missing Concrete | 2 | 1 | l.s. | 500 | 500 | 2500
Auditorium Addition | 72 | Repair Damaged Foundation | 2 | 1 | l.s. | 600 | 600
Auditorium Addition | 73 | Roof (SEE Lib Addn Above) | 1 |  |  |  | 0
Auditorium Addition | 74 | R&R East Doors w/HM Doors | 2 | 2 | ea. | 2500 | 5000
Auditorium Addition | 74 | R&R South Landing | 2 | 1 | l.s. | 3500 | 3500 | 8500
Auditorium Addition | 75 | (SEE Lib Addn Above) | 2 |  |  |  | 0
Auditorium Addition | 76 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1200 | 1200
Auditorium Addition | 78 | Install Exit Signs | 2 | 3 | ea. | 500 | 1500
Auditorium Addition | 79 | Build Enclosed Passage | 3 | 2250 | s.f. | TBD | TBD
Auditorium Addition | 80 | SEE M&E Attached |  |  |  | TBD | TBD |  | 14300
0
Quads Housing | 81 | R&R Settled Walks | 3 | 500 | s.f. | 8 | 4000
Quads Housing | 82 | R&R walk to Commons | 2 | 1 | l.s. | 800 | 800
Quads Housing | 83 | Repair Missing Downspouts | 2 | 7 | ea. | 400 | 2800
Quads Housing | 84 | Adjust Lawn Sprinklers | 1 | 1 | l.s. | 300 | 300
Quads Housing | 84 | Prep/Paint hardboard Siding | 2 | 3400 | s.f. | 2 | 6800 | 7100
Quads Housing | 85 | Shingle Re-Roof Quads | 2 | 14750 | s.f. | 6 | 88500
Quads Housing | 88 | Re-Carpet Commons | 2 | 1220 | s.f. | 6 | 7320
Quads Housing | 89 | Connect Dryers w/ Rigid Duct | 1 | 3 | ea. | 400 | 1200 |  | 111720
0
Pioneer Hall Dorms | 91 | Repair Walk (See 81 above) | 2 | 500 | s.f. | 8 | 4000
Pioneer Hall Dorms | 92 | Replace Missing Downspouts | 1 | 6 | ea. | 350 | 2100
Pioneer Hall Dorms | 92 | Drill French Drains | 3 | 4 | ea. | 2500 | 10000 | 12100
Pioneer Hall Dorms | 93 | Add Roof Access Hatch | 3 | 1 | ea. | 6500 | 6500
Pioneer Hall Dorms | 94 | Adjust Sprinklers | 1 | 1 | l.s. | 400 | 400
Pioneer Hall Dorms | 94 | Repair Siding Trim | 2 | 1 | l.s. | 1500 | 1500
Pioneer Hall Dorms | 94 | Re-Paint Lap Siding | 2 | 7410 | s.f. | 4.15 | 30751.5 | 32251.5 | 55251.5
0
Worforce Readiness Ctr | 96 | R&R Parking lot Walks | 1 | 1300 | s.f. | 8 | 10400
Worforce Readiness Ctr | 96 | Develop S Sewell & Bridge St | 1 |  |  | TBD | TBD
Worforce Readiness Ctr | 97 | Cut and Grade E Side/Sewell | 2 | 21000 | s.f. | 0.65 | 13650
Worforce Readiness Ctr | 97 | Cut & Grade Yard & Bridge St | 2 | 59000 | s.f. | 0.65 | 38350
Worforce Readiness Ctr | 97 | Develop Retention Pond | 2 | 1 | l.s. | 11000 | 11000 | 63000
Worforce Readiness Ctr | 100 | Add Roof Access Hatch | 3 | 1 | ea. | 7500 | 7500
Worforce Readiness Ctr | 100 | Apply Fluid Coating to Roof | 2 | 7240 | s.f. | 4 | 28960
Worforce Readiness Ctr | 100 | Add Insulation w/ ReRoof | 1 | 7240 | s.f. | 3.25 | 23530 | 59990
Worforce Readiness Ctr | 107 | Add Exit Stairs to 2nd Floor | 1 |  |  | TBD | TBD
Worforce Readiness Ctr | 107 | Add Walk Gates to Yard | 2 | 2 | ea. | 1800 | 3600 | 3600
Worforce Readiness Ctr | 108 | Engineer Review CMU-Bents | 1 | 1 | l.s. | 2500 | 2500
Worforce Readiness Ctr | 110 | Sight Barrier Wall w/ Landscape and enlarged yard | 2 | 800 | l.f. | 225 | 180000
Worforce Readiness Ctr | 110 | Addl Gravel For Enlarged Yd. | 2 | 160 | c.y. | 25 | 4000
Worforce Readiness Ctr | 110 | Secure Wheel Stops | 2 | 33 | ea. | 50 | 1650
Worforce Readiness Ctr | 110 | Add Stops at Missing Pkg. | 2 | 6 | ea. | 200 | 1200 | 186850
Worforce Readiness Ctr | 111 | Bore Fiber Opticcable to Main Campus/Admin Bldg. | 2 |  |  | TBD | TBD
Worforce Readiness Ctr | 111 | Develop Paved Walking Path to campus | 2 |  |  | TBD | TBD
[7 empty] | 0 |  | 326340
4659383.5
|  | Total of Identified Items |  |  |  |  | 4659383.5
# NESHAP/HazMat Testing | N.I.C. |  |  | 0
# HazMat Abatement | N.I.C. |  |  | 0
Subtotal Cost |  |  |  | 4659383.5
Contractor Profit |  |  | 10% | 465938.35
Contractor General Conditions |  |  | 6% | 279563.01
Bonds & Insurance |  |  | 2% | 93187.67
Location/Inflation Factor |  |  | 10% | 465938.35
PROBABLE CONTRACT COST…… |  |  |  | 5964010.88
Suggested Construction Contingency |  |  | 5% | 298200.544
A/E Fees |  |  | 10% | 596401.088
Building Permit |  |  | 1.5% | 89460.1632
OVERALL PROJECT COST…….….… |  |  |  | 6948072.6752
# Hazardous material testing is required, costs of testing and abatement are Not In Contract

## Def. Maint. Costs Priority 1
Miles Community College Building Survey 2016 Deferred Maintenance Costs - PRIORITY 1
Location | Summary Item | Description | Priority | Quantity | Unit | Unit Cost | Total | Bldg Subtotal
Classroom & Admin. | 13 | Sidewalk Replacement | 1 | 100 | s.f. | 10 | 1000
Classroom & Admin. | 14 | Add Gutters & Downspouts | 1 | 452 | l.f. | 6 | 2712
Classroom & Admin. | 14 | Re-grade N side of bldg. | 1 | 190 | c.y. | 32 | 6080
Classroom & Admin. | 15 | ReDo Courtyard ramp/walks | 1 | 1 | l.s. | 7500 | 7500
Classroom & Admin. | 15 | Infill W Entry Mud Scrapers | 1 | 2 | ea. | 250 | 500
Classroom & Admin. | 15 | Modify Men's RR Stalls | 1 | 3 | ea. | 1500 | 4500
Classroom & Admin. | 15 | Modify Men's RR Entry | 1 | 1 | ea. | TBD | TBD
Classroom & Admin. | 16 | Coat Roof | 1 | 37332 | s.f. | 4 | 149328 | 171620
Student Services | 27 | Mud Jack E. Café/Bookstore | 1 | 1 | l.s. | 150 | 8000
Student Services | 27 | R&R Kitchen Flooring | 1 | 830 | s.f. | 11 | 9130
Student Services | 30 | R&R Range Hood/Upgrade | 1 | 1 | l.s. | 30000 | 30000
Student Services | 30 | Complete Kitchen Overhaul | 1 | 1 | ea. | TBD | TBD | 47130
Centra | 31 | Repair walks for even grades | 1 | 1 | l.s. | 4000 | 4000
Centra | 31 | Modify Men's RR Stalls | 1 | 2 | ea. | 1500 | 3000
Centra | 31 | Install Exterior Elevator & Shft | 1 | 1 | l.s. | 125000 | 125000
Centra | 31 | R&R Racquetball Doors | 1 | 4 | ea. | 1800 | 7200
Centra | 31 | Install ADA/Braille Signage | 1 | 22 | ea. | 30 | 660
Centra | 34 | Seal wall Penetrations | 1 | 1 | l.s. | 800 | 800
Centra | 39 | Modify Fire Sprinklers | 1 | See M&E |  | TBD | TBD
Centra | 43 | Crows Nest Staircase | 1 | 1 | l.s. | 8500 | 8500
Centra | 43 | Enclose Hall to Crows Nest | 1 | 1 | l.s. | 10000 | 10000
Centra | 43 | HVAC for Crows Nest | 1 | See M&E |  | TBD | TBD | 159160
Vo-Tech | 47 | Modify bottom of Ramp/Gutter | 1 | 1 | l.s. | 2500 | 2500
Vo-Tech | 49 | Replace all windows | 1 | 185 | s.f. | 75 | 13875
Vo-Tech | 51 | New Seals on Exterior Doors | 1 | 10 | ea. | 200 | 2000
Vo-Tech | 51 | Replace OH Doors & Opnrs. | 1 | 3 | ea. | 8500 | 25500
Vo-Tech | 52 | Replace Windows | 1 | 185 | s.f. | 75 | 13875
Vo-Tech | 52 | Replace Fndn. Insulation | 1 | 1968 | s.f. | 4 | 7872
Vo-Tech | 54 | Fix Fire Taping Upper Walls | 1 | 160 | l.f. | 5 | 800
Vo-Tech | 56 | New Door Seals Entry Doors | 1 | 2 | ea. | 250 | 500
Vo-Tech | 56 | New HM Door on Mech Room | 1 | 1 | ea. | 1500 | 1500
Vo-Tech | 56 | Adjust & R&R Closers | 1 | 10 | ea. | 150 | 1500
Vo-Tech | 56 | Electric Door Hold Opens | 1 | 4 | ea. | 1500 | 6000
Vo-Tech | 57 | Install Exit Signs | 1 | 6 | ea. | 500 | 3000
Vo-Tech | 59 | Fixed Mezzanine Stairs | 1 | 2 | ea. | 3500 | 7000 | 85922
Library Addition | 60 | Re-Route Downspout | 1 | 1 | l.s. | 1500 | 1500
Library Addition | 65 | R&R Roof | 1 | 22000 | s.f. | 8.5 | 187000 | 188500
Auditorium Addition | 71 | R&R Settled Walk E Side | 1 | 1 | l.s. | 1200 | 1200
Auditorium Addition | 73 | Roof (SEE Lib Addn Above) | 1 |  |  |  | 0 | 1200
Quads Housing | 84 | Adjust Lawn Sprinklers | 1 | 1 | l.s. | 300 | 300
Quads Housing | 89 | Connect Dryers w/ Rigid Duct | 1 | 3 | ea. | 400 | 1200 | 1500
Pioneer Hall Dorms | 92 | Replace Missing Downspouts | 1 | 6 | ea. | 350 | 2100
Pioneer Hall Dorms | 94 | Adjust Sprinklers | 1 | 1 | l.s. | 400 | 400 | 2500
Worforce Readiness Ctr | 96 | R&R Parking lot Walks | 1 | 1300 | s.f. | 8 | 10400
Worforce Readiness Ctr | 96 | Develop S Sewell & Bridge St | 1 |  |  | TBD | TBD
Worforce Readiness Ctr | 100 | Add Insulation w/ ReRoof | 1 | 7240 | s.f. | 3.25 | 23530
Worforce Readiness Ctr | 107 | Add Exit Stairs to 2nd Floor | 1 |  |  | TBD | TBD
Worforce Readiness Ctr | 108 | Engineer Review CMU-Bents | 1 | 1 | l.s. | 2500 | 2500
TOTAL | [7 empty] | 657532
|  |  |  | TOTAL IDENTIFIED ITEMS |  |  | 657532
# NESHAP/HazMat Testing | N.I.C. |  |  | 0
# HazMat Abatement | N.I.C. |  |  | 0
Subtotal Cost |  |  |  | 657532
Contractor Profit |  |  | 10% | 65753.2
Contractor General Conditions |  |  | 6% | 39451.92
Bonds & Insurance |  |  | 2% | 13150.64
Location/Inflation Factor |  |  | 10% | 65753.2
PROBABLE CONTRACT COST…… |  |  |  | 841640.96
0
Suggested Construction Contingency |  |  | 5% | 42082.048
0
A/E Fees |  |  | 10% | 84164.096
Building Permit |  |  | 1.5% | 12624.6144
OVERALL PRIORITY ONE PROJECT COST…….….… |  |  |  | 980511.7184

## Def. Maint. Costs Priority 2
Miles Community College Building Survey 2016 Deferred Maintenance Costs - PRIORITY 2
Location | Summary Item | Description | Priority | Quantity | Unit | Unit Cost | Total | Bldg Subtotal
Campus & Site | 2 | Develop S Sewell by Track and Centra | 2 | 600 | l.f. | 500 | 300000
Campus & Site | 2 | Develop S Sewell from Batchelor to Comstock | 2 |  |  |  | By City
Campus & Site | 6 | Develop Track Pkg. @ Armory | 2 | 7000 | sf | 10 | 70000
Campus & Site | 6 | Campus Sidewalk Demo & Replacement | 2 | 1500 | s.f. | 12 | 18000 | 388000
Classroom & Admin. | 17 | Replace Entry Systems | 2 | 450 | s.f. | 90 | 40500
Classroom & Admin. | 18 | Insulate Exterior Walls | 2 | 9500 | s.f. | 10 | 95000
Classroom & Admin. | 21 | Pipe insulation & Wrap | 2 | 1 | l.s. | 1500 | 1500
Classroom & Admin. | 21 | Replace HID Wall Packs | 2 | 6 | ea. | 500 | 3000
Classroom & Admin. | 21 | Repair Masonry Sign | 2 | 1 | l.s. | 2500 | 2500 | 142500
Student Services | 22 | E. Sidewalk Replacement | 2 | 400 | s.f. | 8 | 3200
Student Services | 22 | W. Sidewalk Replacement | 2 | 800 | s.f. | 8 | 6400
Student Services | 22 | W. Patio Walk Edge Slope | 2 | 100 | l.f. | 40 | 4000
Student Services | 23 | Engineered Fill E. Side | 2 | 40 | c.y. | 35 | 1400
Student Services | 23 | Relocate W. Roof Drains | 2 | 4 | ea. | 2500 | 10000
Student Services | 24 | Replace W Hall Exterior Brick | 2 | 60 | s.f. | 25 | 1500
Student Services | 24 | R&R E Wainscot Brick | 2 | 380 | s.f. | 35 | 13300
Student Services | 25 | R&R W Alum Entry System | 2 | 132 | s.f. | 90 | 11880
Student Services | 25 | Overhaul E. Doors | 2 | 2 | ea. | 800 | 1600
Student Services | 26 | Adjust N Café Doors | 2 | 2 | ea. | 250 | 500
Student Services | 29 | P&P Kitchen E Wall | 2 | 1 | l.s. | 2500 | 2500
Student Services | 29 | Doorknob Hole W Closet | 2 | 1 | l.s. | 150 | 150 | 56430
Centra | 32 | Change & Extend N Landing | 2 | 70 | s.f. | 8 | 560
Centra | 33 | Eng. Fill and Grade N Side | 2 | 135 | c.y. | 32 | 4320
Centra | 34 | Prep and Paint CMU Walls | 2 | 4600 | s.f. | 3 | 13800
Centra | 34 | Apply EIFS to Lower CMU | 2 | 4600 | s.f. | 14 | 64400
Centra | 34 | Add Insulation to Upper Walls | 2 | 10800 | s.f. | 8 | 86400
Centra | 35 | Replace Windows | 2 | 192 | s.f. | 75 | 14400
Centra | 35 | Exterior Shade for S windows | 2 | 24 | l.f. | 200 | 4800
Centra | 37 | Addition w/ Airlocks to Auditor. | 2 | 1 | ea. | TBD | TBD
Centra | 38 | Replace Main Floor Carpet | 2 | 1664 | s.f. | 6 | 9984
Centra | 38 | Clean & Seal Bare Concrete | 2 | 1 | l.s. | 800 | 800
Centra | 41 | Change Doors to ADA Hrdwr. | 2 | 17 | ea. | 500 | 8500
Centra | 42 | Re-insulate Foundation | 2 | 1600 | s.f. | 6 | 9600 | 217564
Vo-Tech | 46 | R&R Main Entry Landing | 2 | 144 | s.f. | 8 | 1152
Vo-Tech | 46 | Change Door Hrdwr to ADA | 2 | 23 | ea. | 500 | 11500
Vo-Tech | 46 | New Unisex ADA Restroom | 2 | 1 | l.s. | 25000 | 25000
Vo-Tech | 47 | Regrade Landscape to Drain | 2 | 1 | l.s. | 2500 | 2500
Vo-Tech | 52 | Apply EIFS to Exterior Walls | 2 | 7800 | s.f. | 14 | 109200
Vo-Tech | 54 | Prep and Paint Shop Walls | 2 | 7400 | s.f. | 2 | 14800
Vo-Tech | 58 | Replace Damaged Ashpalt | 2 | 500 | s.f. | 8 | 4000
Vo-Tech | 58 | Clean & Seal Asphalt Paving | 2 | 9700 | s.f. | 2.5 | 24250 | 192402
Library Addition | 60 | R&R SW Walk | 2 | 512 | s.f. | 8 | 4096
Library Addition | 61 | Install Heat Tape in Gutter/DS | 2 | 1 | l.s. | 1500 | 1500
Library Addition | 61 | Modify SW corner Landscape | 2 | 1 | l.s. | 1800 | 1800
Library Addition | 62 | Install Roof Hatch & Ladder | 2 | 1 | l.s. | 6500 | 6500
Library Addition | 63 | R&R Panel 15 over Windows | 2 | 520 | s.f. | 20 | 10400
Library Addition | 64 | R&R Windows | 2 | 420 | s.f. | 75 | 31500
Library Addition | 67 | Add Rigid Insulation to Roof | 2 | 22000 | s.f. | 3.25 | 71500
Library Addition | 67 | Insulate Foundation | 2 | 1404 | s.f. | 4 | 5616 | 132912
Auditorium Addition | 71 | Install Splash Blocks | 2 | 8 | ea. | 100 | 800
Auditorium Addition | 71 | Patch in Missing Concrete | 2 | 1 | l.s. | 500 | 500
Auditorium Addition | 72 | Repair Damaged Foundation | 2 | 1 | l.s. | 600 | 600
Auditorium Addition | 74 | R&R East Doors w/HM Doors | 2 | 2 | ea. | 2500 | 5000
Auditorium Addition | 74 | R&R South Landing | 2 | 1 | l.s. | 3500 | 3500
Auditorium Addition | 75 | (SEE Lib Addn Above) | 2 |  |  |  | 0
Auditorium Addition | 78 | Install Exit Signs | 2 | 3 | ea. | 500 | 1500 | 11900
Quads Housing | 82 | R&R walk to Commons | 2 | 1 | l.s. | 800 | 800
Quads Housing | 83 | Repair Missing Downspouts | 2 | 7 | ea. | 400 | 2800
Quads Housing | 84 | Prep/Paint hardboard Siding | 2 | 3400 | s.f. | 2 | 6800
Quads Housing | 85 | Shingle Re-Roof Quads | 2 | 14750 | s.f. | 6 | 88500
Quads Housing | 88 | Re-Carpet Commons | 2 | 1220 | s.f. | 6 | 7320 | 106220
Pioneer Hall Dorms | 91 | Repair Walk (See 81 above) | 2 | 500 | s.f. | 8 | 4000
Pioneer Hall Dorms | 94 | Repair Siding Trim | 2 | 1 | l.s. | 1500 | 1500
Pioneer Hall Dorms | 94 | Re-Paint Lap Siding | 2 | 7410 | s.f. | 4.15 | 30751.5 | 36251.5
Worforce Readiness Ctr | 97 | Cut and Grade E Side/Sewell | 2 | 21000 | s.f. | 0.65 | 13650
Worforce Readiness Ctr | 97 | Cut & Grade Yard & Bridge St | 2 | 59000 | s.f. | 0.65 | 38350
Worforce Readiness Ctr | 97 | Develop Retention Pond | 2 | 1 | l.s. | 11000 | 11000
Worforce Readiness Ctr | 100 | Apply Fluid Coating to Roof | 2 | 7240 | s.f. | 4 | 28960
Worforce Readiness Ctr | 107 | Add Walk Gates to Yard | 2 | 2 | ea. | 1800 | 3600
Worforce Readiness Ctr | 110 | Sight Barrier Wall w/ Landscape and enlarged yard | 2 | 800 | l.f. | 225 | 180000
Worforce Readiness Ctr | 110 | Addl Gravel For Enlarged Yd. | 2 | 160 | c.y. | 25 | 4000
Worforce Readiness Ctr | 110 | Secure Wheel Stops | 2 | 33 | ea. | 50 | 1650
Worforce Readiness Ctr | 110 | Add Stops at Missing Pkg. | 2 | 6 | ea. | 200 | 1200
Worforce Readiness Ctr | 111 | Bore Fiber Opticcable to Main Campus/Admin Bldg. | 2 |  |  | TBD | TBD
Worforce Readiness Ctr | 111 | Develop Paved Walking Path to campus | 2 |  |  | TBD | TBD | 282410
TOTAL | [7 empty] | 1566589.5
|  | Total of Identified Items |  |  |  |  | 1566589.5
# NESHAP/HazMat Testing | N.I.C. |  |  | 0
# HazMat Abatement | N.I.C. |  |  | 0
Subtotal Cost |  |  |  | 1566589.5
Contractor Profit |  |  | 10% | 156658.95
Contractor General Conditions |  |  | 6% | 93995.37
Bonds & Insurance |  |  | 2% | 31331.79
Location/Inflation Factor |  |  | 10% | 156658.95
PROBABLE CONTRACT COST…… |  |  |  | 2005234.56
Suggested Construction Contingency |  |  | 5% | 100261.728
A/E Fees |  |  | 10% | 200523.456
Building Permit |  |  | 1.5% | 30078.5184
OVERALL PROJECT COST…….….… |  |  |  | 2336098.2624
# Hazardous material testing is required, costs of testing and abatement are Not In Contract

## Def. Maint. Costs Priority 3
Miles Community College Building Survey 2016 Deferred Maintenance Costs - PRIORITY 3
Location | Summary Item | Description | Priority | Quantity | Unit | Unit Cost | Total | Bldg Subtotal
Campus & Site | 1 | Develop Moorehead | 3 |  |  |  | By City
Campus & Site | 3 | Bridge St. Curb & Gutter east of S. Sewell N side | 3 | 750 | l.f | 20 | 15000
Campus & Site | 3 | Dedicated bus parking on Bridge St. by track S. side | 3 | 6000 | sf | 25 | 150000
Campus & Site | 3 | Bridge St. Curb & Gutter east of S. Sewell by Track | 3 | 800 | l.f | 20 | 16000
Campus & Site | 8 | Develop French drains, or wells for roof downspouts | 3 | 58 | ea. | 2500 | 145000
Campus & Site | 8 | Grade and develop retention ponds | 3 | 6 | ea. | 7500 | 45000
Campus & Site | 9 | Building Access Controls | 3 | 25 | ea. | 5500 | 137500
Campus & Site | 9 | Outdoor Call Stations | 3 | 7 | ea. | 7000 | 49000
Campus & Site | 9 | Wall Mtd. Call Stations | 3 | 4 | ea. | 3800 | 15200
Campus & Site | 9 | Restrictive Traffic Bollards | 3 | 24 | ea. | 500 | 12000
Campus & Site | 9 | Traffic Gates w/ Access Controls | 3 | 4 | ea. | 9000 | 36000
Campus & Site | 10 | Sidewalk parallel to S. Sewell | 3 | 3500 | sf | 8 | 28000
Campus & Site | 10 | Disc Golf Course | 3 | 18 | ea. | 750 | 13500
Campus & Site | 10 | SE to Track path | 3 | 700 | l.f. | 48 | 33600
Campus & Site | 11 | Modify Irrigation to Drip | 3 | 40 | ea. | 100 | 4000
Campus & Site | 11 | Plant Trees | 3 | 30 | ea. | 400 | 12000
Campus & Site | 12 | Install Generator for Essential systems at Admin., Student Services, Centra | 3 | 3 | ea. | 100000 | 300000
Campus & Site | 12 | Underground LPG storage for Centra, Student Services and Admin | 3 | 5000 | gal | 5 | 25000
Campus & Site | 12 | 100 KW Solar Array & Controller | 3 | 100000 | watt | 1.9 | 190000
Campus & Site | 12 | New Building Sign Package | 3 | 20 | ea. | 1500 | 30000
Campus & Site | 12 | Fix Fence @ Dirt Pkg Lot/Track | 3 | 1 | l.s. | 800 | 800 | 1257600
Classroom & Admin. | 19 | Misc Lay In Clng Replacement | 3 | 1 | l.s. | 8500 | 8500
Classroom & Admin. | 20 | Courtyard Landscape & ReDo | 3 | 1 | l.s. | 30000 | 30000 | 38500
Student Services | 28 | R&R &Raise Kitchen Ceiling | 3 | 830 | s.f. | 5 | 4150 | 4150
Centra | 36 | N Side Gutters & Snow Grds | 3 | 180 | l.f. | 20 | 3600
Centra | 36 | N Side Snow Guards | 3 | 360 | ea. | 10 | 3600
Centra | 36 | Heat Tape all Downspout Ldr | 3 | 10 | ea. | 500 | 5000
Centra | 40 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1500 | 1500
Centra | 44 | Dedicated Track Restrooms | 3 | 2 | ea. | 60000 | 120000
Centra | 45 | Seal East drive & parking | 3 | 3000 | s.f. | 2.5 | 7500 | 141200
Vo-Tech | 48 | Repair or Remove Ext. Walls | 3 | 1 | l.s. | 4500 | 4500
Vo-Tech | 50 | Roof Coating (in 15 yrs out) | 3 | 18570 | s.f. | TBD | TBD
Vo-Tech | 53 | Clean & Caulk Joints | 3 | 448 | l.f. | 4 | 1792
Vo-Tech | 53 | Repair Damaged Sheet Vinyl | 3 | 15 | ea. | 150 | 2250
Vo-Tech | 55 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1500 | 1500
Vo-Tech | 58 | Extend Paving to South | 3 | 24000 | s.f. | 6 | 144000
Vo-Tech | 58 | Fence Around S Lot/Parking | 3 | 500 | l.f. | 30 | 15000 | 169042
Library Addition | 68 | R&R Carpet Library | 3 | 4800 | s.f. | 6 | 28800
Library Addition | 69 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1200 | 1200 | 30000
Auditorium Addition | 76 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1200 | 1200
Auditorium Addition | 79 | Build Enclosed Passage | 3 | 2250 | s.f. | TBD | TBD | 1200
Quads Housing | 81 | R&R Settled Walks | 3 | 500 | s.f. | 8 | 4000 | 4000
Pioneer Hall Dorms | 92 | Drill French Drains | 3 | 4 | ea. | 2500 | 10000
Pioneer Hall Dorms | 93 | Add Roof Access Hatch | 3 | 1 | ea. | 6500 | 6500 | 16500
Worforce Readiness Ctr | 100 | Add Roof Access Hatch | 3 | 1 | ea. | 7500 | 7500
TOTAL | [6 empty] | 0 | 1662192
|  | Total of Identified Items |  |  |  |  | 1662192
# NESHAP/HazMat Testing | N.I.C. |  |  | 0
# HazMat Abatement | N.I.C. |  |  | 0
Subtotal Cost |  |  |  | 1662192
Contractor Profit |  |  | 10% | 166219.2
Contractor General Conditions |  |  | 6% | 99731.52
Bonds & Insurance |  |  | 2% | 33243.84
Location/Inflation Factor |  |  | 10% | 166219.2
PROBABLE CONTRACT COST…… |  |  |  | 2127605.76
Suggested Construction Contingency |  |  | 5% | 106380.288
A/E Fees |  |  | 10% | 212760.576
Building Permit |  |  | 1.5% | 31914.0864
OVERALL PROJECT COST…….….… |  |  |  | 2478660.7104
# Hazardous material testing is required, costs of testing and abatement are Not In Contract

## 10 yr Plan
MILES COMMUNITY COLLEGE DEFERRED MAINTENANCE 10-YEAR MITIGATION PLAN
Deferred Maintenance Category/Location | Summary Item | Description | Priority | Quantity | Unit | Unit Cost | Total | FY2018 Costs | FY2019 Costs | FY2020 Costs | FY2021 Costs | FY2022 Costs | FY2023 Costs | FY2024 Costs | FY2025 Costs | FY2026 Costs
Campus & Site | 1 | Develop Moorehead | 3 |  |  |  | By City
Campus & Site | 2 | Develop S Sewell by Track and Centra | 2 | 600 | l.f. | 500 | 300000
Campus & Site | 2 | Develop S Sewell from Batchelor to Comstock | 2 |  |  |  | By City
Campus & Site | 3 | Bridge St. Curb & Gutter east of S. Sewell N side | 3 | 750 | l.f | 20 | 15000
Campus & Site | 3 | Dedicated bus parking on Bridge St. by track S. side | 3 | 6000 | sf | 25 | 150000
Campus & Site | 3 | Bridge St. Curb & Gutter east of S. Sewell by Track | 3 | 800 | l.f | 20 | 16000
Campus & Site | 5 | Expand S Quads Parking | 3 | 4250 | sf | 10 | 42500
Campus & Site | 5 | Develop East Centra Parking | 3 | 45000 | sf | 10 | 450000
Campus & Site | 6 | Develop Track Pkg. @ Armory | 2 | 7000 | sf | 10 | 70000
Campus & Site | 6 | Campus Sidewalk Demo & Replacement | 2 | 1500 | s.f. | 12 | 18000
Campus & Site | 7 | Campus Outdoor Lighting | 3 | 40 | ea. | 3500 | 140000
Campus & Site | 8 | Develop French drains, or wells for roof downspouts | 3 | 58 | ea. | 2500 | 145000
Campus & Site | 8 | Grade and develop retention ponds | 3 | 6 | ea. | 7500 | 45000
Campus & Site | 9 | Building Access Controls | 3 | 25 | ea. | 5500 | 137500
Campus & Site | 9 | Outdoor Call Stations | 3 | 7 | ea. | 7000 | 49000
Campus & Site | 9 | Wall Mtd. Call Stations | 3 | 4 | ea. | 3800 | 15200
Campus & Site | 9 | Restrictive Traffic Bollards | 3 | 24 | ea. | 500 | 12000
Campus & Site | 9 | Traffic Gates w/ Access Controls | 3 | 4 | ea. | 9000 | 36000
Campus & Site | 10 | Sidewalk parallel to S. Sewell | 3 | 3500 | sf | 8 | 28000
Campus & Site | 10 | Disc Golf Course | 3 | 18 | ea. | 750 | 13500
Campus & Site | 10 | SE to Track path | 3 | 700 | l.f. | 48 | 33600
Campus & Site | 11 | Modify Irrigation to Drip | 3 | 40 | ea. | 100 | 4000
Campus & Site | 11 | Plant Trees | 3 | 30 | ea. | 400 | 12000
Campus & Site | 12 | Install Generator for Essential systems at Admin., Student Services, Centra | 3 | 3 | ea. | 100000 | 300000
Campus & Site | 12 | Underground LPG storage for Centra, Student Services and Admin | 3 | 5000 | gal | 5 | 25000
Campus & Site | 12 | 100 KW Solar Array & Controller | 3 | 100000 | watt | 1.9 | 190000
Campus & Site | 12 | New Building Sign Package | 3 | 20 | ea. | 1500 | 30000
Campus & Site | 12 | Fix Fence @ Dirt Pkg Lot/Track | 3 | 1 | l.s. | 800 | 800
2278100
Classroom & Admin. | 13 | Sidewalk Replacement | 1 | 100 | s.f. | 10 | 1000
Classroom & Admin. | 14 | Add Gutters & Downspouts | 1 | 452 | l.f. | 6 | 2712
Classroom & Admin. | 14 | Re-grade N side of bldg. | 1 | 190 | c.y. | 32 | 6080
Classroom & Admin. | 15 | ReDo Courtyard ramp/walks | 1 | 1 | l.s. | 7500 | 7500
Classroom & Admin. | 15 | Infill W Entry Mud Scrapers | 1 | 2 | ea. | 250 | 500
Classroom & Admin. | 15 | Modify Men's RR Stalls | 1 | 3 | ea. | 1500 | 4500
Classroom & Admin. | 15 | Modify Men's RR Entry | 1 | 1 | ea. | TBD | TBD
Classroom & Admin. | 16 | Coat Roof | 1 | 37332 | s.f. | 4 | 149328
Classroom & Admin. | 17 | Replace Entry Systems | 2 | 450 | s.f. | 90 | 40500
Classroom & Admin. | 18 | Insulate Exterior Walls | 2 | 9500 | s.f. | 10 | 95000
Classroom & Admin. | 19 | Misc Lay In Clng Replacement | 3 | 1 | l.s. | 8500 | 8500
Classroom & Admin. | 21 | Pipe insulation & Wrap | 2 | 1 | l.s. | 1500 | 1500
Classroom & Admin. | 21 | Replace HID Wall Packs | 2 | 6 | ea. | 500 | 3000
Classroom & Admin. | 21 | Repair Masonry Sign | 2 | 1 | l.s. | 2500 | 2500
322620
Student Services | 22 | E. Sidewalk Replacement | 2 | 400 | s.f. | 8 | 3200
Student Services | 22 | W. Sidewalk Replacement | 2 | 800 | s.f. | 8 | 6400
Student Services | 22 | W. Patio Walk Edge Slope | 2 | 100 | l.f. | 40 | 4000
Student Services | 23 | Engineered Fill E. Side | 2 | 40 | c.y. | 35 | 1400
Student Services | 23 | Relocate W. Roof Drains | 2 | 4 | ea. | 2500 | 10000
Student Services | 24 | Replace W Hall Exterior Brick | 2 | 60 | s.f. | 25 | 1500
Student Services | 24 | R&R E Wainscot Brick | 2 | 380 | s.f. | 35 | 13300
Student Services | 25 | R&R W Alum Entry System | 2 | 132 | s.f. | 90 | 11880
Student Services | 25 | Overhaul E. Doors | 2 | 2 | ea. | 800 | 1600
Student Services | 26 | Adjust N Café Doors | 2 | 2 | ea. | 250 | 500
Student Services | 27 | Mud Jack E. Café/Bookstore | 1 | 1 | l.s. | 150 | 8000
Student Services | 27 | R&R Kitchen Flooring | 1 | 830 | s.f. | 11 | 9130
Student Services | 28 | R&R &Raise Kitchen Ceiling | 3 | 830 | s.f. | 5 | 4150
Student Services | 29 | P&P Kitchen E Wall | 2 | 1 | l.s. | 2500 | 2500
Student Services | 29 | Doorknob Hole W Closet | 2 | 1 | l.s. | 150 | 150
Student Services | 30 | R&R Range Hood/Upgrade | 1 | 1 | l.s. | 30000 | 30000
Student Services | 30 | Complete Kitchen Overhaul | 1 | 1 | ea. | TBD | TBD
107710
Centra | 31 | Repair walks for even grades | 1 | 1 | l.s. | 4000 | 4000
Centra | 31 | Modify Men's RR Stalls | 1 | 2 | ea. | 1500 | 3000
Centra | 31 | Install Exterior Elevator & Shft | 1 | 1 | l.s. | 125000 | 125000
Centra | 31 | R&R Racquetball Doors | 1 | 4 | ea. | 1800 | 7200
Centra | 31 | Install ADA/Braille Signage | 1 | 22 | ea. | 30 | 660
Centra | 32 | Change & Extend N Landing | 2 | 70 | s.f. | 8 | 560
Centra | 33 | Eng. Fill and Grade N Side | 2 | 135 | c.y. | 32 | 4320
Centra | 34 | Prep and Paint CMU Walls | 2 | 4600 | s.f. | 3 | 13800
Centra | 34 | Seal wall Penetrations | 1 | 1 | l.s. | 800 | 800
Centra | 34 | Apply EIFS to Lower CMU | 2 | 4600 | s.f. | 14 | 64400
Centra | 34 | Add Insulation to Upper Walls | 2 | 10800 | s.f. | 8 | 86400
Centra | 35 | Replace Windows | 2 | 192 | s.f. | 75 | 14400
Centra | 35 | Exterior Shade for S windows | 2 | 24 | l.f. | 200 | 4800
Centra | 36 | N Side Gutters & Snow Grds | 3 | 180 | l.f. | 20 | 3600
Centra | 36 | N Side Snow Guards | 3 | 360 | ea. | 10 | 3600
Centra | 36 | Heat Tape all Downspout Ldr | 3 | 10 | ea. | 500 | 5000
Centra | 37 | Addition w/ Airlocks to Auditor. | 2 | 1 | ea. | TBD | TBD
Centra | 38 | Replace Main Floor Carpet | 2 | 1664 | s.f. | 6 | 9984
Centra | 38 | Clean & Seal Bare Concrete | 2 | 1 | l.s. | 800 | 800
Centra | 39 | Modify Fire Sprinklers | 1 | See M&E |  | TBD | TBD
Centra | 40 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1500 | 1500
Centra | 41 | Change Doors to ADA Hrdwr. | 2 | 17 | ea. | 500 | 8500
Centra | 42 | Re-insulate Foundation | 2 | 1600 | s.f. | 6 | 9600
Centra | 43 | Crows Nest Staircase | 1 | 1 | l.s. | 8500 | 8500
Centra | 43 | Enclose Hall to Crows Nest | 1 | 1 | l.s. | 10000 | 10000
Centra | 43 | HVAC for Crows Nest | 1 | See M&E |  | TBD | TBD
Centra | 44 | Dedicated Track Restrooms | 3 | 2 | ea. | 60000 | 120000
Centra | 45 | Seal East drive & parking | 3 | 3000 | s.f. | 2.5 | 7500
Centra | 45 | R&R Heavy Pave E. Side |  | 8000 | s.f. | 10 | 80000
597924
Vo-Tech | 46 | R&R Main Entry Landing | 2 | 144 | s.f. | 8 | 1152
Vo-Tech | 46 | Change Door Hrdwr to ADA | 2 | 23 | ea. | 500 | 11500
Vo-Tech | 46 | New Unisex ADA Restroom | 2 | 1 | l.s. | 25000 | 25000
Vo-Tech | 47 | Regrade Landscape to Drain | 2 | 1 | l.s. | 2500 | 2500
Vo-Tech | 47 | Modify bottom of Ramp/Gutter | 1 | 1 | l.s. | 2500 | 2500
Vo-Tech | 48 | Repair or Remove Ext. Walls | 3 | 1 | l.s. | 4500 | 4500
Vo-Tech | 49 | Replace all windows | 1 | 185 | s.f. | 75 | 13875
Vo-Tech | 50 | Roof Coating (in 15 yrs out) | 3 | 18570 | s.f. | TBD | TBD
Vo-Tech | 51 | New Seals on Exterior Doors | 1 | 10 | ea. | 200 | 2000
Vo-Tech | 51 | Replace OH Doors & Opnrs. | 1 | 3 | ea. | 8500 | 25500
Vo-Tech | 52 | Replace Fndn. Insulation | 1 | 1968 | s.f. | 4 | 7872
Vo-Tech | 52 | Apply EIFS to Exterior Walls | 2 | 7800 | s.f. | 14 | 109200
Vo-Tech | 53 | Clean & Caulk Joints | 3 | 448 | l.f. | 4 | 1792
Vo-Tech | 53 | Repair Damaged Sheet Vinyl | 3 | 15 | ea. | 150 | 2250
Vo-Tech | 53 | Replace Vinyl Tile Flooring | 3 | 190 | s.f. | 6 | 1140
Vo-Tech | 54 | Fix Fire Taping Upper Walls | 1 | 160 | l.f. | 5 | 800
Vo-Tech | 54 | Prep and Paint Shop Walls | 2 | 7400 | s.f. | 2 | 14800
Vo-Tech | 55 | Prep and Paint Shop Clngs. |  | 8320 | s.f. | 2 | 16640
Vo-Tech | 55 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1500 | 1500
Vo-Tech | 56 | New Door Seals Entry Doors | 1 | 2 | ea. | 250 | 500
Vo-Tech | 56 | New HM Door on Mech Room | 1 | 1 | ea. | 1500 | 1500
Vo-Tech | 56 | Adjust & R&R Closers | 1 | 10 | ea. | 150 | 1500
Vo-Tech | 56 | Electric Door Hold Opens | 1 | 4 | ea. | 1500 | 6000
Vo-Tech | 57 | Install Exit Signs | 1 | 6 | ea. | 500 | 3000
Vo-Tech | 58 | Replace Damaged Ashpalt | 2 | 500 | s.f. | 8 | 4000
Vo-Tech | 58 | Clean & Seal Asphalt Paving | 2 | 9700 | s.f. | 2.5 | 24250
Vo-Tech | 58 | Extend Paving to South | 3 | 24000 | s.f. | 6 | 144000
Vo-Tech | 58 | Fence Around S Lot/Parking | 3 | 500 | l.f. | 30 | 15000
Vo-Tech | 59 | Fixed Mezzanine Stairs | 1 | 2 | ea. | 3500 | 7000
451271
Library Addition | 60 | Re-Route Downspout | 1 | 1 | l.s. | 1500 | 1500
Library Addition | 60 | R&R SW Walk | 2 | 512 | s.f. | 8 | 4096
Library Addition | 61 | Install Heat Tape in Gutter/DS | 2 | 1 | l.s. | 1500 | 1500
Library Addition | 61 | Modify SW corner Landscape | 2 | 1 | l.s. | 1800 | 1800
Library Addition | 62 | Install Roof Hatch & Ladder | 2 | 1 | l.s. | 6500 | 6500
Library Addition | 63 | R&R Panel 15 over Windows | 2 | 520 | s.f. | 20 | 10400
Library Addition | 64 | R&R Windows | 2 | 420 | s.f. | 75 | 31500
Library Addition | 65 | R&R Roof | 1 | 22000 | s.f. | 8.5 | 187000
Library Addition | 67 | Add Rigid Insulation to Roof | 2 | 22000 | s.f. | 3.25 | 71500
Library Addition | 67 | Insulate Foundation | 2 | 1404 | s.f. | 4 | 5616
Library Addition | 68 | R&R Carpet Library | 3 | 4800 | s.f. | 6 | 28800
Library Addition | 69 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1200 | 1200
351412
Auditorium Addition | 71 | R&R Settled Walk E Side | 1 | 1 | l.s. | 1200 | 1200
Auditorium Addition | 71 | Install Splash Blocks | 2 | 8 | ea. | 100 | 800
Auditorium Addition | 71 | Patch in Missing Concrete | 2 | 1 | l.s. | 500 | 500
Auditorium Addition | 72 | Repair Damaged Foundation | 2 | 1 | l.s. | 600 | 600
Auditorium Addition | 73 | Roof (SEE Lib Addn Above) | 1 |  |  |  | 0
Auditorium Addition | 74 | R&R East Doors w/HM Doors | 2 | 2 | ea. | 2500 | 5000
Auditorium Addition | 74 | R&R South Landing | 2 | 1 | l.s. | 3500 | 3500
Auditorium Addition | 75 | (SEE Lib Addn Above) | 2 |  |  |  | 0
Auditorium Addition | 76 | Replace Damaged Clng Tiles | 3 | 1 | l.s. | 1200 | 1200
Auditorium Addition | 78 | Install Exit Signs | 2 | 3 | ea. | 500 | 1500
Auditorium Addition | 79 | Build Enclosed Passage | 3 | 2250 | s.f. | TBD | TBD
Auditorium Addition | 80 | SEE M&E Attached |  |  |  | TBD | TBD
0
Quads Housing | 81 | R&R Settled Walks | 3 | 500 | s.f. | 8 | 4000
Quads Housing | 82 | R&R walk to Commons | 2 | 1 | l.s. | 800 | 800
Quads Housing | 83 | Repair Missing Downspouts | 2 | 7 | ea. | 400 | 2800
Quads Housing | 84 | Prep/Paint hardboard Siding | 2 | 3400 | s.f. | 2 | 6800
Quads Housing | 85 | Shingle Re-Roof Quads | 2 | 14750 | s.f. | 6 | 88500
Quads Housing | 88 | Re-Carpet Commons | 2 | 1220 | s.f. | 6 | 7320
Quads Housing | 89 | Connect Dryers w/ Rigid Duct | 1 | 3 | ea. | 400 | 1200
0
Pioneer Hall Dorms | 91 | Repair Walk (See 81 above) | 2 | 500 | s.f. | 8 | 4000
Pioneer Hall Dorms | 92 | Replace Missing Downspouts | 1 | 6 | ea. | 350 | 2100
Pioneer Hall Dorms | 92 | Drill French Drains | 3 | 4 | ea. | 2500 | 10000
Pioneer Hall Dorms | 93 | Add Roof Access Hatch | 3 | 1 | ea. | 6500 | 6500
Pioneer Hall Dorms | 94 | Adjust Sprinklers | 1 | 1 | l.s. | 400 | 400
Pioneer Hall Dorms | 94 | Repair Siding Trim | 2 | 1 | l.s. | 1500 | 1500
Pioneer Hall Dorms | 94 | Re-Paint Lap Siding | 2 | 7410 | s.f. | 4.15 | 30751.5
0
Worforce Readiness Ctr | 96 | Develop S Sewell & Bridge St | 1 |  |  | TBD | TBD
Worforce Readiness Ctr | 97 | Cut and Grade E Side/Sewell | 2 | 21000 | s.f. | 0.65 | 13650
Worforce Readiness Ctr | 97 | Cut & Grade Yard & Bridge St | 2 | 59000 | s.f. | 0.65 | 38350
Worforce Readiness Ctr | 97 | Develop Retention Pond | 2 | 1 | l.s. | 11000 | 11000
Worforce Readiness Ctr | 100 | Add Roof Access Hatch | 3 | 1 | ea. | 7500 | 7500
Worforce Readiness Ctr | 100 | Apply Fluid Coating to Roof | 2 | 7240 | s.f. | 4 | 28960
Worforce Readiness Ctr | 100 | Add Insulation w/ ReRoof | 1 | 7240 | s.f. | 3.25 | 23530
Worforce Readiness Ctr | 107 | Add Exit Stairs to 2nd Floor | 1 |  |  | TBD | TBD
Worforce Readiness Ctr | 107 | Add Walk Gates to Yard | 2 | 2 | ea. | 1800 | 3600
Worforce Readiness Ctr | 110 | Sight Barrier Wall w/ Landscape and enlarged yard | 2 | 800 | l.f. | 225 | 180000
Worforce Readiness Ctr | 110 | Addl Gravel For Enlarged Yd. | 2 | 160 | c.y. | 25 | 4000
Worforce Readiness Ctr | 110 | Secure Wheel Stops | 2 | 33 | ea. | 50 | 1650
Worforce Readiness Ctr | 110 | Add Stops at Missing Pkg. | 2 | 6 | ea. | 200 | 1200
Worforce Readiness Ctr | 111 | New Electrical Service | 1 |  |  | TBD | TBD
Worforce Readiness Ctr | 111 | Bore Fiber Opticcable to Main Campus/Admin Bldg. | 2 |  |  | TBD | TBD
Worforce Readiness Ctr | 111 | Develop Paved Walking Path to campus | 2 |  |  | TBD | TBD
Worforce Readiness Ctr | 111 | Demo North Shed | 3 | 1 | l.s. | 500 | 500
**Costs do not include A&E fees, contractor costs, insurance, bonds, inflationary increases, etc. Refer to Priority Lists for more detail.